Project Management Plan

Project: Manage Your Health – Recreation and Wellness System
Prepared By: Vence
Date: 12/1/2025

1. Project Overview

The Manage Your Health project aims to implement a Recreation and Wellness system for company employees to promote health and engagement. This project involves the development, rollout, and training associated with the system, as well as associated incentive programs.

Objectives:

- Deliver a fully functional wellness system for employees.

- Ensure high adoption and engagement through training and incentives.

- Mitigate project risks to ensure on-time and on-budget delivery.

2. Risk Management

2.1 Risk Register

| ID | Risk Description | Type | Probability (1–10) | Impact (1–10) | Risk Score (P×I) | Response Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Key team member leaves the project before completion | Negative | 8 | 9 | 72 | Implement a cross-training team of members |
| 2 | Users remain uncooperative and resistant to using the system | Negative | 7 | 8 | 56 | Conduct user testing and feedback sessions |
| 3 | Team members fail to provide timely status reports | Negative | 6 | 6 | 36 | Establish automated reporting templates and weekly progress check-ins |
| 4 | Successful early rollout of features increases user engagement | Positive | 7 | 9 | 63 | Accelerate deployment of popular features and promote them |
| 5 | The project receives additional funding | Positive | 4 | 7 | 28 | Allocate funds to upgrade system hardware |
| 6 | Integration with HR systems allows better data tracking and reporting | Positive | 6 | 8 | 48 | Collaborate with HR and IT staff to ensure compatibility |

2.2 Risk Assessment Matrix

| Probability \ Impact | Low (1–3) | Medium (4–6) | High (7–10) |
| --- | --- | --- | --- |
| Low (1–3) | Risk 5 |  |  |
| Medium (4–6) |  | Risk 3 | Risk 6 |
| High (7–10) |  | Risk 2 | Risk 1, Risk 4 |

Interpretation:

- High-risk zone: Risk 1, Risk 2, Risk 4 – require immediate attention.

- Moderate-risk zone: Risk 3, Risk 6 – monitor regularly.

- Low-risk zone: Risk 5 – low probability, positive opportunity.

2.3 Risk Response Strategies

Negative Risk Example – Risk 1: Key Team Member Leaving the Project

Strategy: Implement knowledge transfer and cross-training plan to ensure no single person holds critical information.
Implementation Tasks:

- Identify essential knowledge areas and assign secondary owners (4 hours – $200).

- Conduct weekly shadowing sessions for cross-training (8 hours – $400).

- Store key documentation in shared repository (2 hours – $100).

- Review plan monthly and update responsibilities (2 hours – $100).

Total Estimated Cost: $800
Total Estimated Time: 16 hours over one month

Positive Risk Example – Risk 4: Successful Early Rollout of Wellness Features

Strategy: Accelerate deployment of most popular features.
Implementation Tasks:

- Identify and test early-release features with the development team (6 hours – $300).

- Coordinate a pilot launch with a small group of employees (5 hours – $250).

- Create promotional materials and internal newsletters (3 hours – $150).

- Gather feedback and refine before full deployment (6 hours – $300).

Total Estimated Cost: $1,000
Total Estimated Time: 20 hours over two weeks

3. Training and Incentive Program Approach

Recommendation: Keep training in-house while outsourcing the incentive program.

Rationale:

- Internal training leverages existing expertise and ensures long-term system support.

- In-house training allows quick updates, tailored examples, and alignment with actual system usage.

- External support for the incentive program can bring fresh ideas and increase employee engagement.

4. Conclusion

The project’s risk management plan and approach to training/incentives are designed to maximize successful adoption while minimizing disruption. High-priority risks are actively mitigated, and opportunities are pursued to enhance engagement and system success.